## QuickStartPlan
# | Topic | Start_Date | End_Date | Status
1 | Talend Installation in DEV Environment | 2021-01-06 | 2021-01-06 | Completed
2 | Data Integration Basiscs | 2021-07-06 | 2021-08-06
Data Integration in context
Getting Started with Talend Data Integration
Working with Files
Working with Databases
| Using Repository Metadata | 2021-09-06 | 2021-10-06
Processing Data
Using Contexts and Context Variables
Building Executables and Docker Images from Data Integration Jobs
Controlling Execution
Handling Errors
Working with Web Services
3 | Data Integration Advanced | 2021-11-06 | 14/6/2021
Using Git in Talend Studio
Remote Job execution
Basic debugging
Parallel execution
Memorizing data
Joblets
Using Custom Java Code
Change data capture
4 | Talend Data Preparation | 15/6/2021 | 15/6/2021
Data Preparation in context
Creating a data preparation
Using DI for Data Preparation
5 | Talend Data Stewardship | 15/6/2021 | 15/6/2021
Talend Cloud Data Stewardship in context
Resolution campaigns
Grouping campaigns
Arbitration campaigns
Merging campaigns
6 | Talend Data Integration Administration | 16/6/2021 | 17/6/2021
Talend Administration Center
Deploying Jobs
Monitoring the Talend server
Using Git with Talend projects
7 | Best practices on Talend Reference Architecture | 18/6/2021 | 18/6/2021
8 | Real time Use case on Talend Data quality and data integration | 21/6/2021 | 21/6/2021
9 | Implementation of use case-I | 22/6/2021 | 23/6/2021
10 | Implementation of use case-II | 24/6/2021 | 25/6/2021

## 1-Week
Please repeat for each environment
Installation Engineer
Client Contact
| Talend version | 8.0.1
| Cloud/On-Prem | On-Prem
DEV ENVIRONMENT
Product | Item | Completion Dt | Notes | Issue
Nexus | Installation |  | OpenJDK 15.0
Talend Studio | JDK (Optional)
Installation
Xmx memory config
Test Job Creation
Test Job Local run
Test Job - Tested on JobServer
Upload Artifact to Nexus
…
TAC | Installation
User Creation
Project Creation
Project Authorizations
Active Directory/Other
SSL Setup
Git Config
Nexus Config
Job Server config
SMTP, etc
Test Job - Tested from TAC
Memory Config
…
Job Server 1 | Installation
Job Server 2 | Installation
SIT ENVIRONMENT
PROD ENVIRONMENT